## Estimation Record
Area | Description | Size Measure | Typical Effort per Size measure (person/hours) | Size | Effort (person/hours) |  | Final (Fibonacci)
Requirements/Scrum | Definition of users (personas) | # roles | 0.2 | 5 | 1 | 1 | 1
| Definition of User Stories (requirements) | #user stories | 0.4 | 8 | 1 | 3.2 | 5
| Sprint Planning | #user stories | 1 | 8 | 3 | 3 | 13
| Sprint Review | # stories in backlog | 6 | 8 | 3
Config Mgmt | Configuration Items List | # CI Items | 0.09 | 15 | 1 | 1 | 1
Estimation | Estimation Record | # activities | 0.08 | 19 | 1 | 1 | 1
Design | State Transition Diagram | # states | 0.25 | 1 | 1 | 0.25 | 1
| Definition of Use Cases | # use cases | 0.5 | 5 | 1 | 0.5 | 1
| Definitino of Fields | # fields | 0.1 | 3 | 1 | 0.3 | 1
| Definition of Reports | # reports | 1 | 1 | 1 | 1 | 1
| Wireframes | # screens | 0.25 | 4 | 1 | 1 | 1
Coding
| 95778060 (code skeleton story) | # lines of code or markup | 0.25 |  | 1 | 1.25 | 5
| 94752324 (link to profiles story) | # lines of code or markup | 0.25 |  | 1 | 0.75 | 3
| 94877642 (professor social sharing story) | # lines of code or markup | 0.25 |  | 1 | 0.75 | 3
| 94877428 (facilitator view team info) | # lines of code or markup | 0.25 |  | 1 | 0.75 | 3
| 94877362 (site administrator receive registration info) | # lines of code or markup | 0.25 |  | 1 | 0.25 | 1
| 94752508 (student share content) | # lines of code or markup | 0.25 |  | 1 | 0.25 | 1
| 94752348 (view BU twitter feed story) | # lines of code or markup | 0.25 |  | 1 | 0.75 | 3
| 94752336 (student send email to admin) | # lines of code | 0.25 |  | 1 | 1.25 | 5
Peer Reviews
| Issues from Peer Reviews retained | # of issues | 0.16 | 25 | 4 | 4 | 5
Test Design
| Test Cases | # of test cases | 0.33 | 6 | 2 | 2 | 2
Test Execution
| Defects from Testing recorded | # defects | 0.3 | 10 | 3 | 3 | 3

## Version
Version | Date | Person Responsible | Reason
0.1 | 2015-05-30 | Bixby | Initial Draft
1 | 2015-06-20 | Bixby | Final